## Iteration (Sprint) Backlog
Iteration 5 Backlog
day 0 = initial estimate
Requirement | ID | Task Description | Responsible | Cum. Actuals | Status (Not Started / In Progress / Completed) | Estimated hours of work remaining
[6 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 28 | 30
[6 empty] | 2586 | 2582 | 2575 | 2573 | 2393 | 2383 | 2378 | 2357 | 2357 | 2324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formations
Usecase Study | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Design/Coding
|  | Screen Design (Main Screen) - Get it to work |  |  |  | Estimated hours of work remaining 0: 1; Estimated hours of work remaining 1: 1; Estimated hours of work remaining 2: 6; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 12; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Screen Design (Main Screen) - Refine | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | VO Creation |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Screen Design (Zoom Training) - Get it to work |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Screen Design (Zoom Training) - Refine | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Dummy Implementation
Binding Historique Des formations | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Binding Souhaits and the rest of Groups |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | KT from Selva/Hamsa |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementing the methods of Controller Class |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Controller Class
Binding Action components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implementing the methods of Enregistrement Controller |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Business Rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Binding Models with the fields |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing with Manpower test cases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Messages and Validation |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Self Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Code review comments implementation |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Defect Analysis and fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Transactions
INGENP L0
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Write VO for the transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INS61 L0
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Write VO for the transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INS61 A0
Write JUnit test for the transaction. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Write VO for the transaction | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INGNOT L0
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analyse tool tips and Status bar messages of the screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Validating Manpower testcases against Legacy |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Clarifications related to the functionality and test data |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Rework based on the Review comments |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Editions De l'enregistrement (UC-08) GUI only.
|  | Usecase Study |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 0
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
TDD
Identification of GUI components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Package Structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for UI(View) |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Identification of Action components/Mgmt/Rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of Apt action method names |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Identification of Tool Tip message/Status Bar message | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for Controller |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 0
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Coding
|  | Creation of EditionsDeLEnregistrementView |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of EditionsDeLEnregistrementController |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 0
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing Manpower test cases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analyse tool tips and Status bar messages of the screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Validating Manpower testcases against Legacy |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Clarifications related to the functionality and test data |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Rework based on the Review comments |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 0
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Edition du curriculum vitae d'un interimaire
Analysis of Req related doc
|  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of FunctionaL scope |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of CICS/SQL doc |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of Business Rules docs |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of screen flow |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Cross-check functional reqs with legacy |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analyis of VO creation |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Technical Design Doc
|  | View Deign |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Mapping Vos with fields |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Controller and actions |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | check Tooltips and status bar messages from legacy & Image creation |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | psuedo code & French naming convention for methods and variables |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | design approach for certain scenarios |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Coding
Presentation Layer
|  | Edition du CurriculumVitae iMPLEMENTATION of skeleton view |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Creation of first row |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Creation of second row |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Creation of third row |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Creation of Fourth row |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Controller creation & model binding |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implementing actions for menubar & toolbars |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implemention actions other buttons |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | adding attributes to proprty file |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Analyse tool tips and Status bar messages of the screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Application/ Access service
|  | Creation of applicatin & dummy implmeantation |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Unit Testing - Validating against Manpower Test cases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Defect Analysis and Defect Fixing |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Aide Criteres De poste
Analysis of screen flow | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validate the requirements with legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Integration Testing Activities
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Presentation Layer Implementation
View Classes
AideCritereDuPosteView implementation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of view class for Metier tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of View class for Diplomas Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of View class for Criteres Compl tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Metier | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Sec. Br. Spe | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Savoir Faire Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Cond Travel Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Evaluations Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Diplomas Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Justificatifs tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Controller class
Implementation of Controller class for Metier components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of Controller class for Sec. Br. Spe components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of Controller class for Savoir Faire components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of Controller class for Cond Travel components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of Controller class for Evaluations components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation of Controller class for Criteres Compl components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Integration of GCGCTA G0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Access Layer Implementation
Implementation of GCGCTA G0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Unit Testing
|  | Junit Implementation of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing of Poste Criteres against Manpower Test cases. |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Dummy Implementation
|  | Dummy Implementation of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Defect Analysis and fixes
|  | Anticipated defects analysis and fixes. |  |  |  | Estimated hours of work remaining 0: 10; Estimated hours of work remaining 1: 10; Estimated hours of work remaining 2: 10; Estimated hours of work remaining 3: 10; Estimated hours of work remaining 4: 10; Estimated hours of work remaining 5: 10; Estimated hours of work remaining 6: 10; Estimated hours of work remaining 7: 10; Estimated hours of work remaining 8: 10; Estimated hours of work remaining 9: 0
Conditions De Travail
|  | Creation of salary Mask |  |  |  | Estimated hours of work remaining 0: 24; Estimated hours of work remaining 1: 24; Estimated hours of work remaining 2: 24; Estimated hours of work remaining 3: 24; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Integrating TXNs. |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
Testing | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
AideTest
Integration Testing Activities
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Aide List des manpower entries
Coding
self code Review | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Testing
Unit Testing(Manpower Test case) | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
defect Fixing | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Integration Testing Activities
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Aide Conditions De Travail
Implementation
|  | Defect analysis & fixing |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Integrated Transactions for GUI |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Unit testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ32 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for INT075 |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Caching implementation for INT081 |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Integration Testing Activities
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Evaluation
Integration Testing Activities
Testing | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Zoom Test
Coding
|  | Dynamic Mandatory Field check using framework |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Caching implementation for INT086 |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Caching implementation for REQ-55 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ-56 |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Caching implementation for REQ-57 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ-58 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
Testing | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Recherche d'un CI (for Damo User) with transaction
|  | Unit testing |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Defect Fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Action Items for IT2 Retrospective
Separate validation from controller
|  | Module Aide Criteres Du Poste |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Conditions De Travail |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide Test |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide List des manpower entries |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide Conditions De Travail |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Evaluation |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Zoom Test |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Automation of Testcases using QTP/LoFat |  |  |  | Estimated hours of work remaining 0: 80; Estimated hours of work remaining 1: 80; Estimated hours of work remaining 2: 80; Estimated hours of work remaining 3: 80; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Usage of Code revie tool |  |  |  | Estimated hours of work remaining 0: 40; Estimated hours of work remaining 1: 40; Estimated hours of work remaining 2: 40; Estimated hours of work remaining 3: 40; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
Cruise Control Integration | [5 empty] | Estimated hours of work remaining 0: 24; Estimated hours of work remaining 1: 24; Estimated hours of work remaining 2: 24; Estimated hours of work remaining 3: 24; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
New Task
Test Environment SetUP
|  | TRAC and internal defects |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Issue related to save functionality for UC-13 |  | Debugging and fixing.
Issue related to Initialization De la Commande for AppClient. |  | Debugging and fixing.
Test environment setup for testing team |  | For all the three testers
Trouble shooting Remote server (WAS)
Edition Du CV screen in AppClient |  | Edition Du CV screen in AppClient is not opening.
Edition du PreEnregistremnet
Generation of print and preview report (Fiche d'accueil)
|  | Analysis of fuctioning of ireport tool |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
|  | Analysis of flow of code from where the report needs to be generated |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
|  | Analysis of report design |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
|  | Design of report using the ireport tool |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Invocation of jasper reports from the java code using transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementation of report generation using transaction |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
INGTVC
|  | Analysis of CICS txs |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Design of Access service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Design of Application service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Application layer |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Access layer |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | dummy implementation of the txn |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of JUNIT |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration with UI layer |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
INGMTI
|  | Analysis of CICS txs |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Design of Access service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Design of Application service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Application layer |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Access layer |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | dummy implementation of the txn |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of JUNIT |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration with UI layer |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integration of INGPOJ, INGDIP txn with UI |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Writing additional test cases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Liste des CI présélectionnés (UC-14) with integration of transactions (Transactions done by onshore)
Analysis of Req related doc
|  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of FunctionaL scope |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of CICS/SQL doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of Business Rules docs |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of screen flow |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Cross-check functional reqs with legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Technical Design
|  | View design |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Mapping Vos with fields |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Image creation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
check Tooltips and status bar messages from legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | psuedo code |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | design approach for certain scenarios |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | French naming convention for methods and variables |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Presentation Layer
|  | List de CI Preselection iMPLEMENTATION of skeleton view |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | List de CI Preselection implementation of controller |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection - Implementation of properties file |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection - Implementation of Commande group |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | List de CI Preselection - Implementation of Liste de preselections table |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection - Implementation of Liste de proposes table |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection - Implementation of Liste de reserves table |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection - Implementation of Liste de Enleves table |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Validating Manpower testcases against Legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
[6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
[6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Synthèse Intérimaire |  | INGCCI A0 |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of transaction |  |  |  | Estimated hours of work remaining 0: 6; Estimated hours of work remaining 1: 6; Estimated hours of work remaining 2: 6; Estimated hours of work remaining 3: 6; Estimated hours of work remaining 4: 6; Estimated hours of work remaining 5: 6; Estimated hours of work remaining 6: 6; Estimated hours of work remaining 7: 6; Estimated hours of work remaining 8: 6; Estimated hours of work remaining 9: 6
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 6; Estimated hours of work remaining 1: 6; Estimated hours of work remaining 2: 6; Estimated hours of work remaining 3: 6; Estimated hours of work remaining 4: 6; Estimated hours of work remaining 5: 6; Estimated hours of work remaining 6: 6; Estimated hours of work remaining 7: 6; Estimated hours of work remaining 8: 6; Estimated hours of work remaining 9: 6
|  | Implementation of application service |  |  |  | Estimated hours of work remaining 0: 7; Estimated hours of work remaining 1: 7; Estimated hours of work remaining 2: 7; Estimated hours of work remaining 3: 7; Estimated hours of work remaining 4: 7; Estimated hours of work remaining 5: 7; Estimated hours of work remaining 6: 7; Estimated hours of work remaining 7: 7; Estimated hours of work remaining 8: 7; Estimated hours of work remaining 9: 7
|  | Write VOs for the transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
INGCCI A1 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Analysis of transaction |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Implementation of application service | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Write VOs for the transaction |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Aide Criteres De poste |  | Analysis of Req related doc
|  | Analysis of UC - 01, Criteres De Poste |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Analysis of UC - 01, Generel rules | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Analysis of CICS/SQL txn documents |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysis of screen flow |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Validate the requirements with legacy |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Technical Design
Design Main View class for Poste Criteres. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Metier Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Sec. Br. Spe Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Savoir Faire Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Cond Travel Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Evaluations Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Diplomas Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Criteres Compl tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the View class for Justificatifs tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Metier View | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Sec. Br. Spe Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Savoir Faire Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Cond Travel Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Evaluations Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Diplomas Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Criteres Compl tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Justificatifs tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the proerty file for Main View | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Main View components with VOs. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Metier Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Sec. Br. Spe Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Savoir Faire Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Cond Travel Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Evaluations Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Diplomas Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Criteres Compl Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Map Justificatifs Components with respective VO. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Check Tooltips for all the screen components with legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Design the controller class for Criteres De Poste |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Design the Access service for GCGPPO G0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGMDT L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGNPO L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGRPS L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGSPP L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGSAV L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGTES L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGDIP L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGPOJ L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGCTV L0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Access service for GCGCTA G0 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Caching for REQ 46 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Caching for REQ 28 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Caching for REQ 47 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design the Caching for REQ 48 | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Design the application service for Poste Critere |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Writing additional test cases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Presentation Layer Implementation
View Classes
|  | AideCritereDuPosteView implementation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of view class for Metier tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Sec. Br. Spe Tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Savoir Faire Tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Cond Travel Tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Evaluations Tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Diplomas Tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Criteres Compl tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of View class for Justificatifs tab |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Implemetation of Table Decorator for Metier | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Sec. Br. Spe | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Savoir Faire Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Cond Travel Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Evaluations Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Diplomas Tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implemetation of Table Decorator for Justificatifs tab | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Controller class
|  | Implementation of Controller class for Metier components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Sec. Br. Spe components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Savoir Faire components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Cond Travel components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Evaluations components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Diplomas components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Criteres Compl components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of Controller class for Justificatifs components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Application Layer Implementation
|  | Integration of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Integration of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Access Layer Implementation
|  | Caching implementation for REQ 46 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ 28 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ 47 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for REQ 48 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Caching implementation for INT086 |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementation of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementation of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Unit Testing
|  | Junit Implementation of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Junit Implementation of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing of Poste Criteres against Manpower Test cases. |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Dummy Implementation
|  | Dummy Implementation of GCGPPO G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGMDT L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGNPO L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGRPS L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGSPP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGSAV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGTES L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGDIP L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGPOJ L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGCTV L0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy Implementation of GCGCTA G0 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Defect Analysis and fixes
|  | Anticipated defects analysis and fixes. |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Conditions De Travail |  | Analysis of Req related doc
|  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of FunctionaL scope |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analysis of CICS/SQL doc
|  | Analysis of Business Rules docs |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analysis of screen flow | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Cross-check functional reqs with legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Analyis of VO creation |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Technical Design Doc
|  | View Deign |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Mapping Vos with fields | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Controller and actions | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
check Tooltips and status bar messages from legacy & Image creation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
psuedo code & French naming convention for methods and variables | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
design approach for certain scenarios | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Presentation Layer - Implementation
Conditions de travail - skeleton view Implementation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Creation of first column |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of second column |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Placing components according to legasy |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Controller creation & model binding |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementing Enregistrement tab controller abstract methods. |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementing actions |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementing Management rules (2) |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
adding attributes to proprty file | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Creation of salary Mask |  |  |  | Estimated hours of work remaining 0: 24; Estimated hours of work remaining 1: 24; Estimated hours of work remaining 2: 24; Estimated hours of work remaining 3: 24; Estimated hours of work remaining 4: 24; Estimated hours of work remaining 5: 24; Estimated hours of work remaining 6: 24; Estimated hours of work remaining 7: 24; Estimated hours of work remaining 8: 24; Estimated hours of work remaining 9: 24
|  | Integration with Aide screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Defect fixing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Application/ Access service - Implementation
|  | Creation of applicatin & dummy implmeantation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
AideTest |  | Use case study |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Technical Design Document
|  | Identification of Tables |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Clarification of Mapping between Tables | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Identification of VO | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Identification of GUI components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Mapping of components with VO Attributes |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Package structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Pseudocode for UI(View) | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identification of Action Components |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of Management rules |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Creation of appropriate action method names |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of tool tip text |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Pseudocode for controller |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Dummy implementation pseudocode |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Self review | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Coding
|  | Creation of VO's |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Creation of Table decoator. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | View class |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Controller class |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Dummy implementation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
BackLog | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
self code Review | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Caching implementation for REQ-56 |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Testing
|  | Unit Testing(Manpower Test case) |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | defect Fixing |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Writing additional testcases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Aide List des manpower entries |  | Use case study |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Technical Design Document
|  | Identification of Tables |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Clarification of Mapping between Tables |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Identification of VO |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of GUI components |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Mapping of components with VO Attributes |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Package structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for UI(View) |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of Action Components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Identification of Management rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of appropriate action method names |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Identification of tool tip text | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for controller |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy implementation pseudocode |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Self review |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Coding
|  | Creation of VO's |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Creation of Table decoator. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | View class |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Controller class |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Dummy implementation |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
BackLog | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | self code Review |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Testing
|  | Unit Testing(Manpower Test case) |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | defect Fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Writing additional testcases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Aide Conditions De Travail |  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of Functional scope |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analysis of screen flow | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Analysis of business rules |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of messages |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analysis of Vos | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Technical Design Doc
Design the view | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Mapping Vos | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Controller and Actions | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Check tool tips and status bar messages | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Implementation
|  | Implementation of Aide Conditions de Travail view |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Create the controller |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Create the properties file | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implementing the actions |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Creation of dummy implementation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementation of business rules |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | UnitTesting |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Defect analysis & fixing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Writing additional testcases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Evaluation |  | Usecase Study |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
TDD
Identification of Vos | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Identification of GUI components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Mapping of UI components with VO attribute |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Package Structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for UI(View) |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of Action components/Mgmt/Rules |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Creation of Apt action method names |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Identification of Tool Tip message/Status Bar message | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for Controller |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Dummy implementation psuedocode |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Review | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Coding
Creation of ResultatTestInterimaire | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Creation of EvaluationTableDecorator | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Creation of EvaluationView |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Creation of EvaluationController |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Implementation of EnregistrementTabController methods |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dummy implementation |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing Manpower test cases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Defect fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Zoom Test |  | Usecase Study |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
TDD
Identification of GUI components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Mapping of UI components with VO attribute |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Package Structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for UI(View) |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Identification of Action components/Mgmt/Rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of Apt action method names |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Identification of Tool Tip message/Status Bar message | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for Controller |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Coding
|  | Creation of ZoomTestView |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Creation of ZoomTestDialog |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Dummy implementation |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing Manpower test cases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Dynamic Mandatory Field check using framework |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Review of Aide Test |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Defect fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Recherche d'un CI (for Damo User) with transaction
Analysis of usecase documents | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Anaysis of functionalities | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Comparing with Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Modifying the existing View to add required fields |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Adding actions & properties to the fields | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Creating required Vos and creating AccessLayers |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creating Application layers and dummy implementation |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration with UI | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Unit testing |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Defect Fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Cruise Control Integration | [5 empty] | Estimated hours of work remaining 0: 80; Estimated hours of work remaining 1: 80; Estimated hours of work remaining 2: 80; Estimated hours of work remaining 3: 80; Estimated hours of work remaining 4: 80; Estimated hours of work remaining 5: 80; Estimated hours of work remaining 6: 80; Estimated hours of work remaining 7: 80; Estimated hours of work remaining 8: 80; Estimated hours of work remaining 9: 80
Formations |  | Usecase Study |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Design/Coding
|  | Screen Design (Main Screen) - Get it to work |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Screen Design (Main Screen) - Refine |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | VO Creation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Screen Design (Zoom Training) - Get it to work |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Screen Design (Zoom Training) - Refine |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Dummy Implementation
|  | Binding Historique Des formations |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Binding Souhaits and the rest of Groups |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | KT from Selva/Hamsa |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Implementing the methods of Controller Class |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Controller Class
|  | Binding Action components |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implementing the methods of Enregistrement Controller |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Business Rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Binding Models with the fields |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing with Manpower test cases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Messages and Validation |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Self Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Code review comments implementation |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Defect Analysis and fixing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Transactions
INGENP L0
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Write VO for the transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INS61 L0
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Write VO for the transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INS61 A0
Write JUnit test for the transaction. | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implement application service |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Write VO for the transaction | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
INGNOT L0
|  | Integrate with the GUI and test |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Editions De l'enregistrement (UC-08) GUI only.
|  | Usecase Study |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Legacy analysis |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
TDD
Identification of GUI components | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Package Structure | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for UI(View) |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Identification of Action components/Mgmt/Rules |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of Apt action method names |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Identification of Tool Tip message/Status Bar message | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Pseudocode for Controller |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Coding
|  | Creation of EditionsDeLEnregistrementView |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Creation of EditionsDeLEnregistrementController |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Review |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Unit testing Manpower test cases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Clarifications related to the functionality and test data |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Edition du curriculum vitae d'un interimaire
Analysis of Req related doc
|  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of FunctionaL scope |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Analysis of CICS/SQL doc |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of Business Rules docs |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Analysis of screen flow | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Cross-check functional reqs with legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Analyis of VO creation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Technical Design Doc
View Deign | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Mapping Vos with fields | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Controller and actions | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
check Tooltips and status bar messages from legacy & Image creation | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
psuedo code & French naming convention for methods and variables | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
design approach for certain scenarios | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Coding
Presentation Layer
Edition du CurriculumVitae iMPLEMENTATION of skeleton view | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Creation of first row |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Creation of second row |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Creation of third row |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Creation of Fourth row |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Controller creation & model binding |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementing actions for menubar & toolbars |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Implemention actions other buttons |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
adding attributes to proprty file | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Clarifications related to the functionality and test data |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Review of additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Application/ Access service
|  | Creation of applicatin & dummy implmeantation |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Unit Testing - Validating against Manpower Test cases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Defect Analysis and Defect Fixing |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
New Tasks
Recherche Du CI (Task Generation)
Test Environment Setup (For automation of deployment)
Deployment Trobleshooting
Analysis of Trac defects
AppClient setup for Testing team
Action Items
Separate validation from controller
|  | Module Aide Criteres Du Poste |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Conditions De Travail |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide Test |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide List des manpower entries |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Aide Conditions De Travail |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Evaluation |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Module Zoom Test |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Enregistrement –Rules related to Dossier Complete status
|  | Development activities |  |  |  | Estimated hours of work remaining 0: 24; Estimated hours of work remaining 1: 24; Estimated hours of work remaining 2: 24; Estimated hours of work remaining 3: 24; Estimated hours of work remaining 4: 24; Estimated hours of work remaining 5: 24; Estimated hours of work remaining 6: 24; Estimated hours of work remaining 7: 24; Estimated hours of work remaining 8: 24; Estimated hours of work remaining 9: 24
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Validating Manpower testcases against Legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Edition du pré-enregistrement (Edition Profil de compétence)
Generation of print and preview report (Fiche d'accueil)
|  | Analysis of fuctioning of ireport tool |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of flow of code from where the report needs to be generated |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Analysis of report design |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Design of report using the ireport tool |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Invocation of jasper reports from the java code using transaction |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementation of report generation using transaction |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
INGTVC
|  | Analysis of CICS txs |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Design of Access service | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design of Application service | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implementation of Application layer |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implementation of Access layer |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | dummy implementation of the txn |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implementation of JUNIT |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Integration with UI layer |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
INGMTI
|  | Analysis of CICS txs |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Design of Access service | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Design of Application service | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Implementation of Application layer |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implementation of Access layer |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | dummy implementation of the txn |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implementation of JUNIT |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Integration with UI layer |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Integration of INGPOJ, INGDIP txn with UI |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Writing additional test cases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Selection De Profil Metier
Integration Testing Activities
Analysing and Understanding of the screen from the Usecase Document | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Compare the functionality of the screen between Legacy and the UC Doc | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Validating Manpower testcases against Legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Writing additional test cases for the Usecase changes | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Liste des CI présélectionnés (UC-14) with integration of transactions (Transactions done by onshore)
Analysis of Req related doc
|  | Analysis of Use case doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of FunctionaL scope |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of CICS/SQL doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Analysis of Business Rules docs |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Analysis of screen flow | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Cross-check functional reqs with legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Technical Design
|  | View design |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Mapping Vos with fields |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Image creation |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
check Tooltips and status bar messages from legacy | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | psuedo code |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | design approach for certain scenarios |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | French naming convention for methods and variables |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Presentation Layer
|  | List de CI Preselection iMPLEMENTATION of skeleton view |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | List de CI Preselection implementation of controller |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
List de CI Preselection - Implementation of properties file | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
List de CI Preselection - Implementation of Commande group | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
List de CI Preselection - Implementation of Liste de preselections table | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
List de CI Preselection - Implementation of Liste de proposes table | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
List de CI Preselection - Implementation of Liste de reserves table | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
List de CI Preselection - Implementation of Liste de Enleves table | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Integration Testing Activities
|  | Analysing and Understanding of the screen from the Usecase Document |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Compare the functionality of the screen between Legacy and the UC Doc |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Analyse tool tips and Status bar messages of the screen | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Validating Manpower testcases against Legacy |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
Clarifications related to the functionality and test data | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Framing additional testcases |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
Review of additional testcases | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Rework based on the Review comments | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Identifying the testdata required by the Screen |  |  |  | Estimated hours of work remaining 0: 5; Estimated hours of work remaining 1: 5; Estimated hours of work remaining 2: 5; Estimated hours of work remaining 3: 5; Estimated hours of work remaining 4: 5; Estimated hours of work remaining 5: 5; Estimated hours of work remaining 6: 5; Estimated hours of work remaining 7: 5; Estimated hours of work remaining 8: 5; Estimated hours of work remaining 9: 5
|  | Framing the Test cases for CICS Transaction |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Analysing the CICS transactions realted to the screen |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
|  | Testing |  |  |  | Estimated hours of work remaining 0: 8; Estimated hours of work remaining 1: 8; Estimated hours of work remaining 2: 8; Estimated hours of work remaining 3: 8; Estimated hours of work remaining 4: 8; Estimated hours of work remaining 5: 8; Estimated hours of work remaining 6: 8; Estimated hours of work remaining 7: 8; Estimated hours of work remaining 8: 8; Estimated hours of work remaining 9: 8
Updating the defects in defect Tracker | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Generating test Reports | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Analysing trac defects | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Updating the Traceability Matrix | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
Synthèse Intérimaire |  | INGCCI A0
|  | Analysis of transaction |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementation of application service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Write VOs for the transaction |  |  |  | Estimated hours of work remaining 0: 0; Estimated hours of work remaining 1: 0; Estimated hours of work remaining 2: 0; Estimated hours of work remaining 3: 0; Estimated hours of work remaining 4: 0; Estimated hours of work remaining 5: 0; Estimated hours of work remaining 6: 0; Estimated hours of work remaining 7: 0; Estimated hours of work remaining 8: 0; Estimated hours of work remaining 9: 0
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
INGCCI A1
Analysis of transaction | bar: Estimated hours of work remaining 0 to Estimated hours of work remaining 9
|  | Write JUnit test for the transaction. |  |  |  | Estimated hours of work remaining 0: 2; Estimated hours of work remaining 1: 2; Estimated hours of work remaining 2: 2; Estimated hours of work remaining 3: 2; Estimated hours of work remaining 4: 2; Estimated hours of work remaining 5: 2; Estimated hours of work remaining 6: 2; Estimated hours of work remaining 7: 2; Estimated hours of work remaining 8: 2; Estimated hours of work remaining 9: 2
|  | Implementation of application service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3
|  | Write VOs for the transaction |  |  |  | Estimated hours of work remaining 0: 4; Estimated hours of work remaining 1: 4; Estimated hours of work remaining 2: 4; Estimated hours of work remaining 3: 4; Estimated hours of work remaining 4: 4; Estimated hours of work remaining 5: 4; Estimated hours of work remaining 6: 4; Estimated hours of work remaining 7: 4; Estimated hours of work remaining 8: 4; Estimated hours of work remaining 9: 4
|  | Implement Access Service |  |  |  | Estimated hours of work remaining 0: 3; Estimated hours of work remaining 1: 3; Estimated hours of work remaining 2: 3; Estimated hours of work remaining 3: 3; Estimated hours of work remaining 4: 3; Estimated hours of work remaining 5: 3; Estimated hours of work remaining 6: 3; Estimated hours of work remaining 7: 3; Estimated hours of work remaining 8: 3; Estimated hours of work remaining 9: 3

## Idealized Burndown
Idealized Line | day: | 0 | 19
| remaining | 2586 | 0