## Meetings
Product Owner Meeting Notes
Date | Subject | Discusion | Action
Date | SAP kick off | Jan & Mark sow concerns abou the projected enddate(October 2004). The main concerns are the limited time available to develop the desired solution and the state of the discussion within the PCT around data protection, consent and the involved data that will be shared. | Organise kick-off meeting for 1/10 (Jan, Mark, Hubert) Commence discussions on data issues within PCT/S.Serviced (Jan, Mark)
| HIV plans | The HIV project requires a technical proposal: how to work with eForms from tablets, using a local datastore (on the tablet) that synchronises with a central store when a network connection is available. | Contact Ian Muller to discuss technical requirements (Hubert) Draw up development plan (Hubert)
| Additional data load | The data that is loaded into MultiVue needs to be replaced with a most recent set, which can also be extended with fields that were not loaed during the first phase. There is a request to be able to select records using a criterium 'younger then' or 'older then' | Include in plan and estimates (Hubert)
| IRT | The PCT / Soc.Services have a preference for one central MultiVue deployment that services SAP, and in the future IRT type solutions. This is technically cmplex, as the two solutions will dictate very different and stringent security requirements.
| BizTalk 2004 | Hubert raises a request to upgrade BizTalk to the latest version, as it will be an easier and better platform to develop against. | Investigate upgrade possibilities (Jan)
2004-10-01 | Swift demo & review | A discussion on the update frequency of data feeds from npoint systems leads to the conclusion that feeds should be more frequent then once a day. Swift can run updates more often, ePex needs to be investigated. Other notes in the handouts, and incorporated in the updates of the data definitions. | Investigate update frequency from ePex (Jan)
| Swift Care History screens demo & review | The design is documented seperately. General idea is to grow the available historic information by running multiple uploads of data from Swift/ePex to MultiVue/SAP.
| ePex demo & review | All notes are in the handouts, and have been incorporated in the updates of the data defnitions.
| MultiVue demo | Request to broadcast changes, e.g. death of a client. Other remarks are in the action list. | Investigate solution to broadcast changes (Campbell)
| Explicit agreements on datafields to be shared | These are recorded in the data definition tables

## Decisions
Product Owner Decisions
# | Raised | Action | Owner
1 | 2004-10-01 | Data for the Care History table will be loaded from 1st of April, 2004 | Jan/Mark
2
3
4
5
6
7
8
9

## Commitments
Product Owner Commitments
# | Raised | Action | Owner | Ready by | Complete | Remark
1 | 2004-09-20 | Organise kick-off meeting for 1/10 | Jan, Mark, Hubert |  | Ok
2 | 2004-09-20 | Commence discussions on data issues within PCT/S.Services | Jan, Mark |  | Ok
3 | 2004-09-20 | Contact Ian Muller to discuss technical requirements for eForms on a tablet PC | Hubert |  | Ok
4 | 2004-09-20 | Draw up development plan | Hubert |  | Ok
5 | 2004-09-20 | Investigate upgrade possibilities for BizTalk to version 2004 | Jan |  | Ok
6 | 2004-09-20 | Include data reload in plan and estimates | Hubert
7 | 2004-09-20 | Enable select records using a criterium 'younger then' or 'older then' | Hubert |  | Close | No longer a requirement
8 | 2004-10-01 | Investigate update frequency from ePex | Jan |  | Ok | Daily
9 | 2004-10-01 | Investigate solution to broadcast changes e.g. death of a client | Campbell |  | Close | Broadcast not required but show clearly in screen
10 | 2004-10-01 | Search results: add gender | Campbell

## Risks
Risk Log
# | Raised | Description | Impact | Severity | Action | Owner | Complete
1 | 2004-10-21 | Dependency on third party for completion of network configuration. | Delay of go-live date | High | Continuous monitoring | Hubert | No
2 | 2004-11-10 | Planning of training and go-live is unclear. | Poor user preparation for use of the system, impacting on the use of the system and the success of the go-live. | High | Early planning and Preparation | Mark | Yes
3 | 2004-11-10 | Insufficient availability of product owners due to work pressures. | Delay in decisions, preparations and ultimately go-live. | Medium | Continuous monitoring | Hubert | No
Drop down listbox values, don't delete
Severity
High
Medium
Low
Owner
Betty
Campbell
Hubert
Jan
Mark
Pat
Complete
Yes
No

## Project Data
hide this row | Project: Project X phase I | time axis 2004-09-27 to 2005-04-05
| IT Team Tasks |  | days remaining | 125 | 125 | 125 | 125 | 122 | 116 | 116 | 116 | 116 | 113 | 107 | 107 | 106 | 106 | 106 | 97 | 96 | 93 | 92 | 89 | 89 | 89 | 89 | 88 | 87 | 87 | 87 | 87 | 87 | 85 | 81 | 37 | 37 | 37 | 38 | 75 | 33 | 32 | 32 | 32 | 73 | 36 | 36 | 36 | 36 | 71 | 34 | 33 | 33 | 33 | 69 | 44 | 44 | 44 | 44 | 62 | 26 | 25 | 25 | 25 | 60 | 25 | 25 | 25 | 47 | 45 | 45 | 44 | 44 | 45 | 44 | 44 | 44 | 44 | 43 | 43 | 43 | 42 | 42 | 42 | 42 | 42 | 42 | 38 | 14 | 14 | 14 | 13 | 13 | 36 | 13 | 13 | 13 | 13 | 13 | 13 | 30 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hide this line |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154
hide this line |  | Number of consultants: | 1.5 | 125 | 123.5 | 122 | 120.5 | 119 | 117.5 | 116 | 114.5 | 113 | 111.5 | 110 | 108.5 | 107 | 105.5 | 104 | 102.5 | 101 | 99.5 | 98 | 96.5 | 95 | 93.5 | 92 | 90.5 | 89 | 87.5 | 86 | 84.5 | 83 | 81.5 | 80 | 78.5 | 77 | 75.5 | 74 | 72.5 | 71 | 69.5 | 68 | 66.5 | 65 | 63.5 | 62 | 60.5 | 59 | 57.5 | 56 | 54.5 | 53 | 51.5 | 50 | 48.5 | 47 | 45.5 | 44 | 42.5 | 41 | 39.5 | 38 | 36.5 | 35 | 33.5 | 32 | 30.5 | 29 | 27.5 | 26 | 24.5 | 23 | 21.5 | 20 | 18.5 | 17 | 15.5 | 14 | 12.5 | 11 | 9.5 | 8 | 6.5 | 5 | 3.5 | 2 | 0.5 | -1 | -2.5 | -4 | -5.5 | -7 | -8.5 | -10 | -11.5 | -13 | -14.5 | -16 | -17.5 | -19 | -20.5 | -22 | -23.5 | -25 | -26.5 | -28 | -29.5 | -31 | -32.5 | -34 | -35.5 | -37 | -38.5 | -40 | -41.5 | -43 | -44.5 | -46 | -47.5 | -49 | -50.5 | -52 | -53.5 | -55 | -56.5 | -58 | -59.5 | -61 | -62.5 | -64 | -65.5 | -67 | -68.5 | -70 | -71.5 | -73 | -74.5 | -76 | -77.5 | -79 | -80.5 | -82 | -83.5 | -85 | -86.5 | -88 | -89.5 | -91 | -92.5 | -94 | -95.5 | -97 | -98.5 | -100 | -101.5 | -103 | -104.5
| Task description | Responsible | Status | 1000 | 1000 | 1000 | 1000 | 972 | 928 | 928 | 928 | 928 | 900 | 852 | 852 | 844 | 844 | 844 | 776 | 764 | 740 | 732 | 708 | 708 | 708 | 708 | 704 | 696 | 696 | 696 | 692 | 692 | 680 | 644 | 296 | 292 | 292 | 300 | 596 | 260 | 256 | 256 | 256 | 584 | 288 | 284 | 284 | 284 | 564 | 268 | 264 | 264 | 264 | 552 | 352 | 348 | 348 | 348 | 492 | 204 | 200 | 200 | 200 | 480 | 200 | 196 | 196 | 372 | 356 | 356 | 352 | 352 | 360 | 352 | 352 | 348 | 348 | 340 | 340 | 340 | 336 | 336 | 336 | 336 | 336 | 332 | 300 | 108 | 108 | 108 | 104 | 104 | 288 | 104 | 104 | 100 | 100 | 100 | 100 | 240 | 96 | 96 | 96 | 96 | 96 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Component | 7 days | In progress
Status | Project Requirements Gathering | Campbell | In progress | 1: 32; 2: 32; 3: 32; 4: 32; 5: 24; 6: 24; 7: 24; 8: 24; 9: 24; 10: 24; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 24; 17: 24; 18: 24; 19: 24; 20: 24; 21: 24; 22: 24; 23: 24; 24: 24; 25: 24; 26: 24; 27: 24; 28: 24; 29: 24; 30: 24; 31: 24; 32: 24; 33: 24; 34: 24; 35: 24; 36: 24; 41: 16; 42: 16; 43: 16; 44: 16; 45: 16; 46: 16; 47: 16; 48: 16; 49: 16; 50: 16; 51: 16; 52: 16; 53: 16; 54: 16; 55: 16; 56: 16; 61: 8; 65: 8; 66: 8; 67: 8; 68: 8; 69: 8; 70: 8; 71: 8; 72: 8; 73: 8; 74: 8; 75: 8; 76: 8; 77: 8; 78: 8; 79: 8; 80: 8; 81: 8; 82: 8; 83: 8; 84: 8; 90: 8; 97: 8
Not started | Formal Requirements Documentation | Campbell | In progress | 1: 24; 2: 24; 3: 24; 4: 24; 5: 24; 6: 24; 7: 24; 8: 24; 9: 24; 10: 24; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 24; 17: 24; 18: 24; 19: 24; 20: 24; 21: 24; 22: 24; 23: 24; 24: 24; 25: 24; 26: 24; 27: 24; 28: 24; 29: 24; 30: 24; 31: 24; 32: 24; 33: 24; 34: 24; 35: 24; 36: 24; 41: 16; 42: 16; 43: 16; 44: 16; 45: 16; 46: 16; 47: 16; 48: 16; 49: 16; 50: 16; 51: 16; 52: 16; 53: 16; 54: 16; 55: 16; 56: 16; 61: 16; 65: 8; 66: 8; 67: 8; 68: 8; 69: 8; 70: 8; 71: 8; 72: 8; 73: 8; 74: 8; 75: 8; 76: 8; 77: 8; 78: 8; 79: 8; 80: 8; 81: 8; 82: 8; 83: 8; 84: 8; 90: 8; 97: 8
In progress | MultiVue Configuration Component | 2 days | Not started
Completed | Append Additional Demographics | Campbell | Completed | 1: 16; 2: 16; 3: 16; 4: 16; 5: 16; 6: 16; 7: 16; 8: 16; 9: 16; 10: 16; 11: 16; 12: 16; 13: 16; 14: 16; 15: 16; 16: 16; 17: 16; 18: 16; 19: 16; 20: 16; 21: 16; 22: 16; 23: 16; 24: 16; 25: 16; 26: 16; 27: 16; 28: 16; 29: 16; 30: 16; 31: 16; 36: 16; 41: 16; 46: 16; 51: 16; 56: 16; 61: 16; 65: 16; 70: 8; 74: 8; 75: 0
| SAP Component | 60 days | In progress
| Design SAP Database | Campbell | Completed | 1: 16; 2: 16; 3: 16; 4: 16; 5: 12; 6: 16; 7: 16; 8: 16; 9: 16; 10: 12; 11: 12; 12: 12; 13: 12; 14: 12; 15: 12; 16: 12; 17: 8; 18: 8; 19: 8; 20: 8; 21: 8; 22: 8; 23: 8; 24: 8; 25: 4; 26: 4; 27: 4; 28: 4; 29: 4; 30: 0; 31: 0; 35: 0
| Creation of the SAP Database | Campbell | Completed | 1: 24; 2: 24; 3: 24; 4: 24; 5: 24; 6: 24; 7: 24; 8: 24; 9: 24; 10: 24; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 12; 17: 12; 18: 12; 19: 12; 20: 12; 21: 12; 22: 12; 23: 12; 24: 12; 25: 12; 26: 12; 27: 12; 28: 12; 29: 12; 30: 12; 31: 8; 35: 8; 36: 8; 40: 0; 41: 0
| Create stored procedures on SAP database | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 32; 11: 32; 12: 32; 13: 32; 14: 32; 15: 32; 16: 20; 17: 20; 18: 20; 19: 20; 20: 20; 21: 20; 22: 20; 23: 20; 24: 20; 25: 20; 26: 20; 27: 20; 28: 20; 29: 20; 30: 16; 31: 12; 35: 0; 36: 0
| Creation of SAP .NET Component | Campbell | Completed | 1: 104; 2: 104; 3: 104; 4: 104; 5: 104; 6: 64; 7: 64; 8: 64; 9: 64; 10: 64; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 32; 17: 32; 18: 24; 19: 16; 20: 8; 21: 8; 22: 8; 23: 8; 24: 8; 25: 8; 26: 8; 27: 8; 28: 8; 29: 8; 30: 8; 31: 0; 35: 0
| Creation of SAP Web Application | Campbell | Completed | 1: 64; 2: 64; 3: 64; 4: 64; 5: 64; 6: 64; 7: 64; 8: 64; 9: 64; 10: 64; 11: 64; 12: 64; 13: 64; 14: 64; 15: 64; 16: 52; 17: 52; 18: 52; 19: 52; 20: 52; 21: 52; 22: 52; 23: 52; 24: 52; 25: 48; 26: 48; 27: 48; 28: 48; 29: 48; 30: 44; 31: 24; 35: 0; 36: 0
| Creation of Security Administration Site | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 32; 7: 32; 8: 32; 9: 32; 10: 32; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 16; 17: 12; 18: 8; 19: 8; 20: 0; 21: 0
| Secure Messenging | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 32; 7: 32; 8: 32; 9: 32; 10: 32; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 16; 17: 12; 18: 8; 19: 8; 20: 0; 21: 0
| Security Integration | Campbell | Completed | 1: 24; 2: 24; 3: 24; 4: 24; 5: 24; 6: 16; 7: 16; 8: 16; 9: 16; 10: 16; 11: 8; 12: 8; 13: 8; 14: 8; 15: 8; 16: 0; 17: 0; 18: 0; 19: 0; 20: 0; 21: 0
| SAP system testing | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40; 19: 40; 20: 40; 21: 40; 22: 40; 23: 40; 24: 40; 25: 40; 26: 40; 27: 40; 28: 40; 29: 40; 30: 40; 31: 40; 36: 32; 37: 32; 38: 32; 39: 32; 40: 32; 41: 32; 46: 24; 47: 24; 48: 24; 49: 24; 50: 24; 51: 24; 52: 24; 53: 24; 54: 24; 55: 24; 56: 24; 61: 24; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 16; 90: 8; 97: 0
| SAP System Verification | Campbell | In progress | 1: 16; 2: 16; 3: 16; 4: 16; 5: 16; 6: 16; 7: 16; 8: 16; 9: 16; 10: 16; 11: 16; 12: 16; 13: 16; 14: 16; 15: 16; 16: 16; 17: 16; 18: 16; 19: 16; 20: 16; 21: 16; 22: 16; 23: 16; 24: 16; 25: 16; 26: 16; 27: 16; 28: 16; 29: 16; 30: 16; 31: 16; 32: 16; 33: 16; 34: 16; 35: 16; 36: 16; 41: 32; 42: 32; 43: 32; 44: 32; 45: 32; 46: 32; 47: 32; 48: 32; 49: 32; 50: 32; 51: 32; 52: 32; 53: 32; 54: 32; 55: 32; 56: 32; 57: 32; 58: 32; 59: 32; 60: 32; 61: 32; 62: 32; 63: 32; 64: 32; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 16; 90: 16; 97: 8
| Bug Fixing / Cosmetic Changes | Campbell | In progress | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40; 19: 40; 20: 40; 21: 40; 22: 40; 23: 40; 24: 40; 25: 40; 26: 40; 27: 40; 28: 40; 29: 40; 30: 40; 31: 40; 32: 40; 33: 40; 34: 40; 35: 40; 36: 40; 37: 40; 38: 40; 39: 40; 40: 40; 41: 40; 42: 40; 43: 40; 44: 40; 45: 40; 46: 32; 51: 24; 52: 24; 53: 24; 54: 24; 55: 24; 56: 24; 61: 24; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 16; 90: 16; 97: 16
| Install in Live Environment | Campbell | In progress | 1: 16; 2: 16; 3: 16; 4: 16; 5: 16; 6: 16; 7: 16; 8: 16; 9: 16; 10: 16; 11: 16; 12: 16; 13: 16; 14: 16; 15: 16; 16: 16; 17: 16; 18: 16; 19: 16; 20: 16; 21: 16; 22: 16; 23: 16; 24: 16; 25: 16; 26: 16; 27: 16; 28: 16; 29: 16; 30: 16; 31: 16; 32: 16; 33: 16; 34: 16; 35: 16; 36: 16; 37: 16; 38: 16; 39: 16; 40: 16; 41: 16; 42: 16; 43: 16; 44: 16; 45: 16; 46: 16; 47: 16; 48: 16; 49: 16; 50: 16; 51: 16; 52: 16; 53: 16; 54: 16; 55: 16; 56: 16; 57: 16; 58: 16; 59: 16; 60: 16; 61: 16; 62: 16; 63: 16; 64: 16; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 16; 90: 8; 97: 4
| Go Live Support | Campbell | Not started | 1: 16; 2: 16; 3: 16; 4: 16; 5: 16; 6: 16; 7: 16; 8: 16; 9: 16; 10: 16; 11: 16; 12: 16; 13: 16; 14: 16; 15: 16; 16: 16; 17: 16; 18: 16; 19: 16; 20: 16; 21: 16; 22: 16; 23: 16; 24: 16; 25: 16; 26: 16; 27: 16; 28: 16; 29: 16; 30: 16; 31: 16; 32: 16; 33: 16; 34: 16; 35: 16; 36: 16; 37: 16; 38: 16; 39: 16; 40: 16; 41: 16; 42: 16; 43: 16; 44: 16; 45: 16; 46: 16; 47: 16; 48: 16; 49: 16; 50: 16; 51: 16; 52: 16; 53: 16; 54: 16; 55: 16; 56: 16; 57: 16; 58: 16; 59: 16; 60: 16; 61: 16; 62: 16; 63: 16; 64: 16; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 16; 90: 16; 97: 16
| General Project Component | 25 days | In progress
| Project Management | Hubert | In progress | 144 | 144 | 144 | 144 | 128 | 144 | 144 | 144 | 144 | 128 | 128 | 128 | 120 | 120 | 120 | 120 | 120 | 112 | 112 | 112 | 112 | 112 | 112 | 108 | 108 | 108 | 108 | 104 | 104 | 104 | 104 | 104 | 100 | 100 | 100 | 100 | 100 | 96 | 96 | 96 | 96 | 96 | 92 | 92 | 92 | 92 | 92 | 88 | 88 | 88 | 88 | 88 | 84 | 84 | 84 | 84 | 84 | 80 | 80 | 80 | 80 | 80 | 76 | 76 | 76 | 76 | 76 | 72 | 72 | 72 | 72 | 72 | 68 | 68 | 68 | 68 | 68 | 64 | 64 | 64 | 64 | 64 | 60 | 60 | 60 | 60 | 60 | 56 | 56 | 56 | 56 | 56 | 52 | 52 | 52 | 52 | 52 | 48 | 48 | 48 | 48 | 48 | 44
| System Documentation | Campbell | Not started | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| User Documentation | Campbell | Not started | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
| BizTalk 2004 Component | 31 days | Not started
Resources | Extend ePEX-3 Adaptor | Campbell | In progress | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40; 19: 40; 20: 40; 21: 40; 22: 40; 23: 40; 24: 40; 25: 40; 26: 40; 27: 40; 28: 40; 29: 40; 30: 40; 31: 40; 36: 40; 41: 40; 46: 40; 51: 40; 56: 32; 61: 32; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 8; 90: 16; 97: 8
Campbell | Extend Swift Adaptor | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40; 19: 40; 20: 40; 21: 40; 22: 40; 23: 40; 24: 40; 25: 40; 26: 40; 27: 40; 28: 40; 29: 40; 30: 40; 31: 40; 36: 40; 41: 40; 46: 40; 51: 40; 56: 40; 61: 40; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 71: 0; 72: 0; 73: 0
Hubert | Extend Upstream Schemas | Campbell | Completed | 1: 8; 2: 8; 3: 8; 4: 8; 5: 8; 6: 8; 7: 8; 8: 8; 9: 8; 10: 8; 11: 8; 12: 8; 13: 8; 14: 8; 15: 8; 16: 8; 17: 8; 18: 8; 19: 8; 20: 8; 21: 8; 22: 8; 23: 8; 24: 8; 25: 8; 26: 8; 27: 8; 28: 8; 29: 8; 30: 8; 31: 8; 36: 8; 41: 8; 46: 8; 51: 8; 56: 8; 61: 8; 65: 8; 66: 8; 67: 8; 68: 8; 69: 8; 70: 8; 71: 8; 72: 8; 73: 8; 74: 8; 75: 8; 76: 8; 77: 8; 78: 8; 79: 8; 80: 8; 81: 8; 82: 8; 83: 8; 84: 8; 90: 0
Jan | Create AIC schema | Campbell | Completed | 1: 8; 2: 8; 3: 8; 4: 8; 5: 8; 6: 8; 7: 8; 8: 8; 9: 8; 10: 8; 11: 8; 12: 8; 13: 8; 14: 8; 15: 8; 16: 8; 17: 8; 18: 8; 19: 8; 20: 8; 21: 8; 22: 8; 23: 8; 24: 8; 25: 8; 26: 8; 27: 8; 28: 8; 29: 8; 30: 8; 31: 8; 36: 8; 41: 8; 46: 8; 51: 8; 56: 8; 61: 8; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 71: 0; 72: 0; 73: 0
Jan/Mark | Create Mappings | Campbell | In progress | 1: 24; 2: 24; 3: 24; 4: 24; 5: 24; 6: 24; 7: 24; 8: 24; 9: 24; 10: 24; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 24; 17: 24; 18: 24; 19: 24; 20: 24; 21: 24; 22: 24; 23: 24; 24: 24; 25: 24; 26: 24; 27: 24; 28: 24; 29: 24; 30: 24; 31: 24; 36: 24; 41: 24; 46: 24; 51: 24; 56: 16; 61: 16; 65: 8; 66: 8; 67: 8; 68: 8; 69: 8; 70: 8; 71: 8; 72: 8; 73: 8; 74: 8; 75: 8; 76: 8; 77: 8; 78: 8; 79: 8; 80: 8; 81: 8; 82: 8; 83: 8; 84: 8; 90: 8; 97: 8
Mark | Create SAP AIC | Campbell | Completed | 1: 64; 2: 64; 3: 64; 4: 64; 5: 64; 6: 64; 7: 64; 8: 64; 9: 64; 10: 64; 11: 64; 12: 64; 13: 64; 14: 64; 15: 64; 16: 64; 17: 64; 18: 64; 19: 64; 20: 64; 21: 64; 22: 64; 23: 64; 24: 64; 25: 64; 26: 64; 27: 64; 28: 64; 29: 64; 30: 64; 31: 64; 36: 64; 41: 64; 46: 64; 51: 64; 56: 24; 61: 24; 65: 16; 66: 16; 67: 16; 68: 16; 69: 16; 70: 16; 71: 16; 72: 16; 73: 16; 74: 16; 75: 16; 76: 16; 77: 16; 78: 16; 79: 16; 80: 16; 81: 16; 82: 16; 83: 16; 84: 8; 90: 8; 97: 0
Mike | Unit Testing | Campbell | Completed | 1: 40; 2: 40; 3: 40; 4: 40; 5: 40; 6: 40; 7: 40; 8: 40; 9: 40; 10: 40; 11: 40; 12: 40; 13: 40; 14: 40; 15: 40; 16: 40; 17: 40; 18: 40; 19: 40; 20: 40; 21: 40; 22: 40; 23: 40; 24: 40; 25: 40; 26: 40; 27: 40; 28: 40; 29: 40; 30: 40; 31: 40; 36: 40; 41: 40; 46: 40; 51: 40; 52: 40; 53: 40; 54: 40; 55: 40; 56: 40; 61: 40; 65: 40; 66: 40; 67: 40; 68: 40; 69: 40; 70: 40; 71: 40; 72: 40; 73: 40; 74: 40; 75: 40; 76: 40; 77: 40; 78: 40; 79: 40; 80: 40; 81: 40; 82: 40; 83: 40; 84: 24; 90: 32; 97: 24
| Integration Documentation | Campbell | Not started | 1: 24; 2: 24; 3: 24; 4: 24; 5: 24; 6: 24; 7: 24; 8: 24; 9: 24; 10: 24; 11: 24; 12: 24; 13: 24; 14: 24; 15: 24; 16: 24; 17: 24; 18: 24; 19: 24; 20: 24; 21: 24; 22: 24; 23: 24; 24: 24; 25: 24; 26: 24; 27: 24; 28: 24; 29: 24; 30: 24; 31: 24; 36: 24; 41: 24; 46: 24; 51: 24; 52: 24; 53: 24; 54: 24; 55: 24; 56: 24; 61: 24; 65: 40; 66: 40; 67: 40; 68: 40; 69: 40; 70: 40; 71: 40; 72: 40; 73: 40; 74: 40; 75: 40; 76: 40; 77: 40; 78: 40; 79: 40; 80: 40; 81: 40; 82: 40; 83: 40; 84: 40; 90: 40; 97: 40
Product Owner Tasks | time axis 2004-09-27 to 2005-04-05
keep hidden | Task description | Responsible | Status | 2004-09-27 | 2004-09-28 | 2004-09-29 | 2004-09-30 | 2004-10-01 | 2004-10-04 | 2004-10-05 | 2004-10-06 | 2004-10-07 | 2004-10-08 | 2004-10-11 | 2004-10-12 | 2004-10-13 | 2004-10-14 | 2004-10-15 | 2004-10-18 | 2004-10-19 | 2004-10-20 | 2004-10-21 | 2004-10-22 | 2004-10-25 | 2004-10-26 | 2004-10-27 | 2004-10-28 | 2004-10-29 | 2004-11-01 | 2004-11-02 | 2004-11-03 | 2004-11-04 | 2004-11-05 | 2004-11-08 | 2004-11-09 | 2004-11-10 | 2004-11-11 | 2004-11-12 | 2004-11-15 | 2004-11-16 | 2004-11-17 | 2004-11-18 | 2004-11-19 | 2004-11-22 | 2004-11-23 | 2004-11-24 | 2004-11-25 | 2004-11-26 | 2004-11-29 | 2004-11-30 | 2004-12-01 | 2004-12-02 | 2004-12-03 | 2004-12-06 | 2004-12-07 | 2004-12-08 | 2004-12-09 | 2004-12-10 | 2004-12-13 | 2004-12-14 | 2004-12-15 | 2004-12-16 | 2004-12-17 | 2004-12-20 | 2004-12-21 | 2004-12-22 | 2004-12-23 | 2004-12-24 | 2005-01-01 | 2005-01-02 | 2005-01-03 | 2005-01-04 | 2005-01-05 | 2005-01-08 | 2005-01-09 | 2005-01-10 | 2005-01-11 | 2005-01-12 | 2005-01-15 | 2005-01-16 | 2005-01-17 | 2005-01-18 | 2005-01-19 | 2005-01-22 | 2005-01-23 | 2005-01-24 | 2005-01-25 | 2005-01-26 | 2005-01-27 | 2005-01-28 | 2005-01-29 | 2005-01-30 | 2005-01-31 | 2005-02-01 | 2005-02-02 | 2005-02-03 | 2005-02-04 | 2005-02-05 | 2005-02-06 | 2005-02-07 | 2005-02-08 | 2005-02-09 | 2005-02-10 | 2005-02-11 | 2005-02-12 | 2005-02-13 | 2005-02-14 | 2005-02-15 | 2005-02-16 | 2005-02-17 | 2005-02-18 | 2005-02-19 | 2005-02-20 | 2005-02-21 | 2005-02-22 | 2005-02-23 | 2005-02-24 | 2005-02-25 | 2005-02-26 | 2005-02-27 | 2005-02-28 | 2005-03-01 | 2005-03-02 | 2005-03-03 | 2005-03-04 | 2005-03-05 | 2005-03-06 | 2005-03-07 | 2005-03-08 | 2005-03-09 | 2005-03-10 | 2005-03-11 | 2005-03-12 | 2005-03-13 | 2005-03-14 | 2005-03-15 | 2005-03-16 | 2005-03-17 | 2005-03-18 | 2005-03-19 | 2005-03-20 | 2005-03-21 | 2005-03-22 | 2005-03-23 | 2005-03-24 | 2005-03-25 | 2005-03-26 | 2005-03-27 | 2005-03-28 | 2005-03-29 | 2005-03-30 | 2005-03-31 | 2005-04-01 | 2005-04-02 | 2005-04-03 | 2005-04-04 | 2005-04-05
| Design tasks |  | In progress
| Data mapping: Swift to SAP | Mark | Completed
| Data mapping: ePex to SAP | Jan | Completed
| Data mapping: Care History to SAP | Jan/Mark | Completed
| Training preparation |  | In progress
| Agree scheduling with Project Board | Jan/Mark | In progress
Prepare trainer materials
Prepare handouts
Prepare exercises
Prepare training data
Run trial training
Appoint trainers
Complete training schedule
Schedule dates early to avoid clashes
Determine group size
Determine format and duration of hands-on session
| Network Configuration |  | In progress
| Design network structure | Jan/Mark | In progress
| Order components | Jan/Mark | In progress
Issue installation requests to service providers
Monitor completion of installation
Test network components
Test end-to-end services
Test SAP application over the network
| Go-live preparation |  | In progress
| Agree dates with Project Board | Mark | In progress
Design vetting process
Distribute user authorisations
Add input of user secrets to training
| Train and prepare support staff | Mark
Update existing support processes
User acceptance testing
Data loadng
Note on E4: This number is used to calculate the 'ideal line' in the burndown chart.
Note on F3: calculated number of worked days in the sprint
Note on F4: Calculated number ofwork days left in the sprint. Used to draw the 'ideal line'
Note on F43: This customer didn't track work left for the product owners. It would require a second burndown chart.
Note on A7: Used for drop down list box in column 'Status'
Note on A30: Used for drop down listbox in column 'responsible'
Note on AO10: My burndown sheet updates became a weekly exercise. The chart now shows spikes. For customer presentation purposes I hide empty columns in this worksheet, that makes the graph smooth.