## Sprint Backlog
Core - Sprint 16 Backlog
| Team: | 8
| Days: | 10 | Sprint Start Date: | 2006-09-25
| Hours: | 44.8 | Sprint End Date: | 2006-10-06
| Max Hrs: | 358.4
|  |  | Working Days Left: |  |  |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
Remaining Effort in Hours
# | Gemini | Item | Task | Status | P1 | P2 | 2006-09-25 | 2006-09-26 | 2006-09-27 | 2006-09-28 | 2006-09-29 | 2006-10-02 | 2006-10-03 | 2006-10-04 | 2006-10-05 | 2006-10-06
[7 empty] | 344 | 317 | 248 | 226 | 176 | 176 | 120 | 93 | 22 | 8
1 |  | Complete XXX Page (continued)
2 |  | licensing (design only) |  | Complete | CJ | CC | 40 | 37 | 32 | 16 | 16 | 16 | 8 | 0.5
3 |  | Field visibility (tech design) |  | In Progress | SB | CJ | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 4 | 1
4 |  | Remove side panel & implement tabs |  | Complete | GB | AM | 24 | 20
5 |  | Lookups (dropdowns, lookups, datepicker)
6 |  |  | Classification Code implementation | Complete | SB | GB | 32 | 27 | 23 | 8
7 |  |  | Lookup control build | Complete | SB | GB |  |  |  | 32 | 24 | 24 | 8
8 |  |  | UI Testing | In Progress | CA | [8 empty] | 8 | 6 | 4
9 |  |  | Documentation | In Progress | GB | [8 empty] | 8 | 8 | 2
10 |  | Web partification |  | Complete | GB |  | 8 | 5 | 8
11 |  | AAA Use Cases
12 |  |  | ABC Management | Complete | RG | AT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
13 |  |  | Personal Information Management | Complete | RG | AT | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
14 |  |  | Address Management | Complete | RG | AT | 36 | 36 | 32 | 24 | 16 | 16 | 12 | 6
15 |  |  | DEF Management (scenario 1) | Complete | RG | AT | 8 | 8 | 5 | 5 | 4 | 4 | 4 | 4
16
17
Individual Hours
[6 empty] | CJ | 60 | 57 | 52 | 36 | 36 | 36 | 28 | 20.5 | 4 | 1
| Colours | Not Started |  |  |  | SB | 52 | 47 | 43 | 60 | 44 | 44 | 28 | 20 | 4 | 1
|  | In Progress |  |  |  | CC | 40 | 37 | 32 | 16 | 16 | 16 | 8 | 0.5 | 0 | 0
|  | Complete |  |  |  | AM | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Deferred |  |  |  | GB | 64 | 52 | 31 | 40 | 24 | 24 | 8 | 8 | 8 | 2
|  | Testing |  |  |  | CA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 4
| Tasks | Summary of Item |  |  |  | TV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Line Item |  |  |  | RG | 52 | 52 | 45 | 37 | 28 | 28 | 24 | 18 | 0 | 0
|  | Support Item |  |  |  | AT | 52 | 52 | 45 | 37 | 28 | 28 | 24 | 18 | 0 | 0
[6 empty] | ST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Day |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  |  |  | Linear |  |  | 344 | 322.5 | 279.5 | 258.5 | 211.5 | 164.5 | 117.5 | 73.5 | 24.5 | -24.5
|  |  |  | Adjustments |  |  | 4: 32; 8: 16
Support Used
Support Available