## idealized line
iteration | 0 | 8
remaining | 3291 | 0

## Product Backlog
| Product Backlog | baseline date: 26-05-2006 |  | #REF!
| Level-1 Requirement Description (very preferable user-centric features or use cases; would the customer pay for this?). | Level-2 Requirement (very preferably user-centric). Tasks to implement this user-centric goal belong in an ITERATION BACKLOG, not here! | Donor | Comments (e.g., dependencies, customer …) | Entry date | ID | Order | Scope (MoSCoW) | Risk (1,2,3) | Biz Value | Rel. Effort | Status (pending, underway, complete, cancelled) | Completed in iter# | Cum. Actuals | Initial Est. | Iteration# and estimated person-days of effort remaining until completion
[15 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[14 empty] | 0 | 3291 | 3272 | 3210 | 2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Current
Iter #3
| UC 01 | Aide Critères de Poste | [12 empty] | Initial Est. 0: 46; Iteration# and estimated person-days of effort remaining until completion 1: 46; Iteration# and estimated person-days of effort remaining until completion 2: 46; Iteration# and estimated person-days of effort remaining until completion 3: 46
|  | Aide Conditions de travail | [12 empty] | Initial Est. 0: 6; Iteration# and estimated person-days of effort remaining until completion 1: 6; Iteration# and estimated person-days of effort remaining until completion 2: 6; Iteration# and estimated person-days of effort remaining until completion 3: 6
|  | Aide Liste des entités manpower | [12 empty] | Initial Est. 0: 14; Iteration# and estimated person-days of effort remaining until completion 1: 14; Iteration# and estimated person-days of effort remaining until completion 2: 14; Iteration# and estimated person-days of effort remaining until completion 3: 14
|  | Aide Test | [12 empty] | Initial Est. 0: 9; Iteration# and estimated person-days of effort remaining until completion 1: 9; Iteration# and estimated person-days of effort remaining until completion 2: 9; Iteration# and estimated person-days of effort remaining until completion 3: 9
|  | Commentaires Synthèse Entretien | [12 empty] | Initial Est. 0: 11; Iteration# and estimated person-days of effort remaining until completion 1: 11; Iteration# and estimated person-days of effort remaining until completion 2: 11; Iteration# and estimated person-days of effort remaining until completion 3: 11
|  | Sélection de profil métier | [12 empty] | Initial Est. 0: 11; Iteration# and estimated person-days of effort remaining until completion 1: 11; Iteration# and estimated person-days of effort remaining until completion 2: 11; Iteration# and estimated person-days of effort remaining until completion 3: 11
|  | Zoom Test | [12 empty] | Initial Est. 0: 5; Iteration# and estimated person-days of effort remaining until completion 1: 5; Iteration# and estimated person-days of effort remaining until completion 2: 5; Iteration# and estimated person-days of effort remaining until completion 3: 5
| UC 13 | Edition du pré-enregistrement | [12 empty] | Initial Est. 0: 47; Iteration# and estimated person-days of effort remaining until completion 1: 47; Iteration# and estimated person-days of effort remaining until completion 2: 47; Iteration# and estimated person-days of effort remaining until completion 3: 47
| UC 08 | Recherche d'un CI | [12 empty] | Initial Est. 0: 32; Iteration# and estimated person-days of effort remaining until completion 1: 32; Iteration# and estimated person-days of effort remaining until completion 2: 32; Iteration# and estimated person-days of effort remaining until completion 3: 32
|  | Enregistrement | [12 empty] | Initial Est. 0: 38; Iteration# and estimated person-days of effort remaining until completion 1: 38; Iteration# and estimated person-days of effort remaining until completion 2: 38; Iteration# and estimated person-days of effort remaining until completion 3: 38
|  | Missions (Assignments) | [12 empty] | Initial Est. 0: 23; Iteration# and estimated person-days of effort remaining until completion 1: 23; Iteration# and estimated person-days of effort remaining until completion 2: 23; Iteration# and estimated person-days of effort remaining until completion 3: 23
|  | Conditions de travail | [12 empty] | Initial Est. 0: 9; Iteration# and estimated person-days of effort remaining until completion 1: 9; Iteration# and estimated person-days of effort remaining until completion 2: 9; Iteration# and estimated person-days of effort remaining until completion 3: 9
|  | Evaluation | [12 empty] | Initial Est. 0: 14; Iteration# and estimated person-days of effort remaining until completion 1: 14; Iteration# and estimated person-days of effort remaining until completion 2: 14; Iteration# and estimated person-days of effort remaining until completion 3: 14
|  | Formations (Trainings) | [12 empty] | Initial Est. 0: 29; Iteration# and estimated person-days of effort remaining until completion 1: 29; Iteration# and estimated person-days of effort remaining until completion 2: 29; Iteration# and estimated person-days of effort remaining until completion 3: 29
|  | EDITIONS DE L'ENREGISTREMENT | [12 empty] | Initial Est. 0: 9; Iteration# and estimated person-days of effort remaining until completion 1: 9; Iteration# and estimated person-days of effort remaining until completion 2: 9; Iteration# and estimated person-days of effort remaining until completion 3: 9
Finer
Grained,
Better
Analyzed
| UC 06 | EDITION DU CURRICULUM VITAE D’UN INTERIMAIRE | [12 empty] | Initial Est. 0: 24; Iteration# and estimated person-days of effort remaining until completion 1: 24; Iteration# and estimated person-days of effort remaining until completion 2: 24; Iteration# and estimated person-days of effort remaining until completion 3: 24
|  | Aperçu Du CV avant impression (Print Preview) | [12 empty] | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 3; Iteration# and estimated person-days of effort remaining until completion 2: 3; Iteration# and estimated person-days of effort remaining until completion 3: 3
| UC 14 | Liste des CI présélectionnés | [12 empty] | Initial Est. 0: 44; Iteration# and estimated person-days of effort remaining until completion 1: 44; Iteration# and estimated person-days of effort remaining until completion 2: 44; Iteration# and estimated person-days of effort remaining until completion 3: 44
|  | Sauvegarde de la commande | [12 empty] | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 3; Iteration# and estimated person-days of effort remaining until completion 2: 3; Iteration# and estimated person-days of effort remaining until completion 3: 3
|  | Liste des commandes | [12 empty] | Initial Est. 0: 15; Iteration# and estimated person-days of effort remaining until completion 1: 15; Iteration# and estimated person-days of effort remaining until completion 2: 15; Iteration# and estimated person-days of effort remaining until completion 3: 15
|  | Initialisation de la commande | [12 empty] | Initial Est. 0: 24; Iteration# and estimated person-days of effort remaining until completion 1: 24; Iteration# and estimated person-days of effort remaining until completion 2: 24; Iteration# and estimated person-days of effort remaining until completion 3: 24
|  | Liste des CI-Présélectionné | [12 empty] | Initial Est. 0: 62; Iteration# and estimated person-days of effort remaining until completion 1: 62; Iteration# and estimated person-days of effort remaining until completion 2: 62; Iteration# and estimated person-days of effort remaining until completion 3: 62
|  | Suppression d'une commande | [12 empty] | Initial Est. 0: 12; Iteration# and estimated person-days of effort remaining until completion 1: 12; Iteration# and estimated person-days of effort remaining until completion 2: 12; Iteration# and estimated person-days of effort remaining until completion 3: 12
Coarser | UC 7 | [13 empty] | Initial Est. 0: 375; Iteration# and estimated person-days of effort remaining until completion 1: 375; Iteration# and estimated person-days of effort remaining until completion 2: 375; Iteration# and estimated person-days of effort remaining until completion 3: 325
Grained, | UC 16 | [13 empty] | Initial Est. 0: 475; Iteration# and estimated person-days of effort remaining until completion 1: 475; Iteration# and estimated person-days of effort remaining until completion 2: 475; Iteration# and estimated person-days of effort remaining until completion 3: 450
Less | UC 19 | [13 empty] | Initial Est. 0: 550; Iteration# and estimated person-days of effort remaining until completion 1: 550; Iteration# and estimated person-days of effort remaining until completion 2: 550; Iteration# and estimated person-days of effort remaining until completion 3: 500
Well | UC 9 | [13 empty] | Initial Est. 0: 475; Iteration# and estimated person-days of effort remaining until completion 1: 475; Iteration# and estimated person-days of effort remaining until completion 2: 475; Iteration# and estimated person-days of effort remaining until completion 3: 425
Analyzed | UC 15 | [13 empty] | Initial Est. 0: 550; Iteration# and estimated person-days of effort remaining until completion 1: 550; Iteration# and estimated person-days of effort remaining until completion 2: 550; Iteration# and estimated person-days of effort remaining until completion 3: 500
Complete
| UC 01 | CNIL Wizard & Motcles | [10 empty] | 3 |  | Initial Est. 0: 6; Iteration# and estimated person-days of effort remaining until completion 1: 6; Iteration# and estimated person-days of effort remaining until completion 2: 6; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Recherche du client | [10 empty] | 3 |  | Initial Est. 0: 30; Iteration# and estimated person-days of effort remaining until completion 1: 30; Iteration# and estimated person-days of effort remaining until completion 2: 30; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Liste des CD rattachés au SIRET | [10 empty] | 3 |  | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 3; Iteration# and estimated person-days of effort remaining until completion 2: 3; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Saisie des pièces justificatives à fournir | [10 empty] | 3 |  | Initial Est. 0: 29; Iteration# and estimated person-days of effort remaining until completion 1: 29; Iteration# and estimated person-days of effort remaining until completion 2: 29; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide ETT | [10 empty] | 3 |  | Initial Est. 0: 12; Iteration# and estimated person-days of effort remaining until completion 1: 12; Iteration# and estimated person-days of effort remaining until completion 2: 12; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide Diplome | [10 empty] | 3 |  | Initial Est. 0: 17; Iteration# and estimated person-days of effort remaining until completion 1: 17; Iteration# and estimated person-days of effort remaining until completion 2: 17; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | List De Poste | [10 empty] | 3 |  | Initial Est. 0: 18; Iteration# and estimated person-days of effort remaining until completion 1: 18; Iteration# and estimated person-days of effort remaining until completion 2: 18; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide Nationalite | [10 empty] | 3 |  | Initial Est. 0: 8; Iteration# and estimated person-days of effort remaining until completion 1: 8; Iteration# and estimated person-days of effort remaining until completion 2: 8; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Zoom Meteir Screen | [10 empty] | 1 |  | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide Meteir Screen | [10 empty] | 1 |  | Initial Est. 0: 5; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide Specialites Screen | [10 empty] | 1 |  | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide SECTUEURS BRANCHES | [10 empty] | 1 |  | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide COMMUNE | [10 empty] | 1 |  | Initial Est. 0: 3; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Aide Department | [10 empty] | 1 |  | Initial Est. 0: 2; Iteration# and estimated person-days of effort remaining until completion 1: 0; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
| UC 13 | Validation Du Pré-Enregistrement | [10 empty] | 3 |  | Initial Est. 0: 51; Iteration# and estimated person-days of effort remaining until completion 1: 51; Iteration# and estimated person-days of effort remaining until completion 2: 51; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | List of Homonymes | [10 empty] | 2 |  | Initial Est. 0: 24; Iteration# and estimated person-days of effort remaining until completion 1: 24; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Pre-Enregistrement | [10 empty] | 2 |  | Initial Est. 0: 38; Iteration# and estimated person-days of effort remaining until completion 1: 38; Iteration# and estimated person-days of effort remaining until completion 2: 0; Iteration# and estimated person-days of effort remaining until completion 3: 0
| UC 08 | Aptitudes | [10 empty] | 3 |  | Initial Est. 0: 24; Iteration# and estimated person-days of effort remaining until completion 1: 24; Iteration# and estimated person-days of effort remaining until completion 2: 24; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Bloc-Notes | [10 empty] | 3 |  | Initial Est. 0: 5; Iteration# and estimated person-days of effort remaining until completion 1: 5; Iteration# and estimated person-days of effort remaining until completion 2: 5; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Etat-Civil | [10 empty] | 3 |  | Initial Est. 0: 20; Iteration# and estimated person-days of effort remaining until completion 1: 20; Iteration# and estimated person-days of effort remaining until completion 2: 20; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Métier | [10 empty] | 3 |  | Initial Est. 0: 20; Iteration# and estimated person-days of effort remaining until completion 1: 20; Iteration# and estimated person-days of effort remaining until completion 2: 20; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Paiement | [10 empty] | 3 |  | Initial Est. 0: 33; Iteration# and estimated person-days of effort remaining until completion 1: 33; Iteration# and estimated person-days of effort remaining until completion 2: 33; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Justificatifs | [10 empty] | 3 |  | Initial Est. 0: 30; Iteration# and estimated person-days of effort remaining until completion 1: 30; Iteration# and estimated person-days of effort remaining until completion 2: 30; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Expérience | [10 empty] | 3 |  | Initial Est. 0: 23; Iteration# and estimated person-days of effort remaining until completion 1: 23; Iteration# and estimated person-days of effort remaining until completion 2: 23; Iteration# and estimated person-days of effort remaining until completion 3: 0
|  | Diplômes | [10 empty] | 3 |  | Initial Est. 0: 18; Iteration# and estimated person-days of effort remaining until completion 1: 18; Iteration# and estimated person-days of effort remaining until completion 2: 18; Iteration# and estimated person-days of effort remaining until completion 3: 0
| Total of Orig Estimates of Complete Reqs | [13 empty] | Initial Est. 0: 428
| Current Release Totals | [12 empty] | 0 | 3291 | 3272 | 3210 | 2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEXT
RELEASE
Cancelled
375
475
550
475
550
Note on A40: Near future requirements are more fine-grained, often with level-1 and level-2 breakdown.
Note on A70: Distant requirements are coarse-grained, often without a level-2 breakdown.
Note on A172: The product backlog is for ALL future backlog, across all releases. However, some companies dump far-future wishes in some other req tracking tool, and they don't have to be copied here.
Note on A180: Some teams need to keep track of this; some cancelled items may move on to the 'next release' backlog
Note on B1: craig.larman: This structure will always mutate into something unique for your project needs… I like to collect new examples that people find useful. Please send me your examples to craig@craiglarman.com
Note on B2: 80% of items may be far-future iteration goals, larger in effort and more vague. 20% of items may be near-future iteration goals, and finer-grained in effort (e.g., 15 person days) and more detailed. A use case is a set of related scenarios of things a user does to achieve some goal. e.g., Download and Play Video In most requirement systems, a "feature" is a preferably user-centric functional req that is not expressable as a use case, or is a non-functional req. e.g., 'implement MM7 protocol', 'implement report-5', 'internationalize for swedish and french'.
Note on C1: the 'entry date' of reqs relates to this baseline date: all reqs added before XXX will be part of the baseline
Note on C2: Don't decompose requirements more than these two levels! This section may be empty for the 80% far-future Level-1 requirements, and usually filled in for the 20% near-future fine-grained requirements. Also, a level-2 req in the current iteration should be small enough to COMPLETE within the iteration.
Note on F2: relates to baseline date: reqs entered before baseline date XXX are in the baseline set
Note on G2: Every requirement should have an ID. At level 1 and at level 2. These IDs are good to reference in automated acceptance and unit tests, to support traceability.
Note on H2: force-rank order 1..N of some of the requirements (not necessarily all of them)
Note on I2: What is in/out for the UPCOMING RELEASE? Avoid more than 50% of team capacity for release allocated to 'Must' requirements. Read about the "MoSCOW" scope system on the Web at http://en.wikipedia.org/wiki/MoSCoW_Method
Note on J2: Technical or architecture risk or importance. More complex is possible; is more complex useful or believable? 1 = lowest risk
Note on K2: Scrum encourages considering BV as a factor in priority. BV methods? 1) distribute 1000 points of BV across reqs; 2) relative point estimation with estimation poker method; 3) distribute total estimated revenue across items (hard)
Note on L2: NOT an "absolute" effort in time. Rather, a relative point estimate in 'story points', H/M/L, or fibonnaci points (1, 2, 3, 5, 8, 13). if points, 1 = lowest/least effort
Note on N2: some find it useful to be able to track historical progress iteration by iteration. this captures it.