## PRODUCT BACKLOG
*** Priority is calculated using Wiegers Relative Weighting Approach
Benefit / Penalty Scale 1 (low) - 9 (high)
PRODUCT BACKLOG
ID | STORY / FEATURE / REQUEST | CATEGORY | TYPE | Relative Benefit | Relative Penalty | Total Value | Value % | Estimate | Cost % | *** Priority
1 | As the system I want to be able to capture image files from disk | Imaging | Feature | 9 | 9 | 18 | 22.2222 | 10 | 10.4167 | 2.1333 | Feature
7 | As a user when I enter a non alphanumeric character when logging in an error occurs | Login | Bug | 2 | 1 | 3 | 3.7037 | 2 | 2.0833 | 1.7778 | Bug
2 | As a user I want to be able to view the metadata for an image | Index | Feature | 7 | 3 | 10 | 12.3457 | 8 | 8.3333 | 1.4815
3 | As the system when an image appears on disk I want to automatically capture it | Imaging | Feature | 8 | 9 | 17 | 20.9877 | 15 | 15.625 | 1.3432
4 | As a user I want to be able to login to the system | Login | Feature | 3 | 5 | 8 | 9.8765 | 8 | 8.3333 | 1.1852
5 | As a user when I have logged in I want to view my inbox | Desktop | Feature | 9 | 2 | 11 | 13.5802 | 21 | 21.875 | 0.62081
6 | As a user I want to be able to view a scanned document | Imaging | Feature | 8 | 6 | 14 | 17.284 | 32 | 33.3333 | 0.51852
| TOTALS |  |  | 46 | 35 | 81 | 100 | 96 | 100

## RISK LOG
RISK DESCRIPTION | Severity | Notes
Request response time from vendor X will slow down teams momentum | Critical
Technical knowledge of hibernate is lacking | High | 3 day hibernate course was held prior to initiation

## IMPEDIMENTS
IMPEDIMENT | RAISED ON | RAISED BY | STATUS | NOTES
Details for image capture are not coming through quick enough, lack of cooperation with SME's | 2006-07-12 | GSM | Open | Have escalated this to steering committee to ensure that prompt responses when details are requested takes place

## SPRINT REVIEW ¦ RETROSPECTIVES
GUIDELINES: What should we as a team start doing? What should we as a team stop doing? What should we as a team keep doing? Did we achieve the sprint goal?
SPRINT 1
SPRINT 2
SPRINT 3

## SPRINT 1 - BACKLOG
SPRINT 1
GOAL
Lorem ipsum tibique patrioque disputationi at nec, ei eam semper gubergren. Ne duo atqui dictas feugiat, ea mea suscipit sententiae complectitur. Nusquam contentiones ut cum, offendit invenire et quo. His cu dicam labores quaestio.At vix sale prompta, ullum honestatis cotidieque et usu. No quodsi impedit nam. Eam at virtute assentior temporibus, ad pri fuisset apeirian atomorum. Mei ea tollit suscipiantur. Mel no possim postulant aliquando, facer choro ne ius.
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
ITEM DESCRIPTION | WHO? | Hours of Effort Remaining ---> | 362 | 354 | 342 | 332 | 332 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322 | 322
322
Story A
Task 1 | GSM | 40 | 40 | 32 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task 2 | MSP | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Task 3 | GSM | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Task 4 | MSP | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Task 5 | JA | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Task 6 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Task 7 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Task 8 |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Task 9 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Story B
Task 1 |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Task 2 |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Task 3 |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Note on D10: gms: This displays the number of hours remaining. Adjust this each day to reflect how long you think there is still left. When a task is completed then set all other days to 0