## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2006-06-13 | 42 | 2006-07-24 | 19
2 | 2006-07-25 | 42 | 2006-09-04 | 0
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2006-06-13 | 14 | 2006-06-26 | 8 | Planned |  | Planning | 1
2 | 2006-06-27 | 14 | 2006-07-10 | 3 | Planned |  | Specification and prototype development | 1
3 | 2006-07-11 | 14 | 2006-07-24 | 8 | Planned |  | Specification and prototype development | 1
4 | 2006-07-25 | 14 | 2006-08-07 | 0 | Planned |  | Specification and prototype development | 2
5 | 2006-08-08 | 14 | 2006-08-21 | 0 | Planned |  | Specification and prototype development, documentation | 2
6 | 2006-08-22 | 14 | 2006-09-04 | 0 | Planned |  | Usability test, documentation, prototype corrections | 2
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 13
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | This is a sample story | Done | 3 | 1
2 | This is another sample story | Ongoing | 5 | 1 |  | You can add comments here to add key detail or explanation to the story. For larger definitions, use external tools and materials.
3 | This is a third sample story | Planned | 3 | 2
4 | This is a fourth sample story | Planned | 8 | 3
5 | This is an unallocated sample story | Planned | 13
6 | This is a removed story | Removed | 5
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.
Sort Product Backlog

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 7 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 33 | 33 | 30 | 23 | 21
Task rows | 4 | Done days | 4 |  | 33 | 26.4 | 19.8 | 13.2 | 6.6
Warning! These are necessary |  | Trend |  |  | 33.2 | 28.9 | 24.6 | 20.3 | 16 | 11.7 | 7.4 | 3.1
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 33.2 1: 1; 28.9 2: 2; 24.6 3: 3; 20.3 4: 4; 16 5: 5
Example task | 1 | Danny Dev | Done | 5 | 33.2 1: 5; 28.9 2: 2; 24.6 3: 0
Example task 2 | 1 | Tina Tester | Ongoing | 7 | 33.2 1: 7; 28.9 2: 7; 24.6 3: 2; 20.3 4: 2
Example task 3 | 2 | Danny Dev | Ongoing | 12 | 33.2 1: 12; 28.9 2: 12; 24.6 3: 12; 20.3 4: 10
<Delete these example lines> | 2 |  | Planned | 9 | 33.2 1: 9; 28.9 2: 9; 24.6 3: 9; 20.3 4: 9
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.
Sort Sprint Tasks
Update Task Slips

## Sprint Sheet Template
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.
Sort Sprint Tasks
Update Task Slips

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
Responsible Person: Danny Dev
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: Tina Tester
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: Danny Dev
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person:
Initial Estimate | 9 | Work Done |  | Work Left